## Sheet1
Date | Comments
2018-03-03 | Worked on the Voltage inputs to Cells
CB | Set up VC5x inputs
Tested for Transistor types
2018-03-07 | Completed the Batt output with 2N3906 transistor in it.
CB | Added 2N3906 transistor Datasheet to components file
2018-03-08 | Created High Power Circuit and added terminal blocks, power supply, motor controller terminal blocks, and battery input
TS
2018-03-08 | Added SENSE_R global variable to sense resistor circuit. Changed BJTs to MOSFET equivalents. Also added text, descriptions for different blocks of circuit.
TS
2018-03-09 | Finsihed Battery Management IC Connections and Double Checked them.
CB | Added information on Microcontroller Inputs.
Posted question underneath High Power Circuit.
2018-03-09 | Changed the external power block to 20 pin and added BATT+ and BATT- to terminals 19 and 20 so the external power circuit will have the ability to use 24V
TS
2018-03-10 | Deleted the external power block as there is no need for anything low voltage to be connected to the back. Also linked footprints to all the capacitors. Created the BOM we will be using for the board
TS
2018-03-11 | Removed connection between BATT- and GND. Had to replace BATT- with GND on some 24V terminal Blocks.
TS
2018-03-11 | Deleted Barrel jack 12V power connections after talking to Carl. Deemed unecessary.
TS
2018-03-21 | Started PCBnew. changed footprints to my kicad's format. Layed out the general format for the pcb board. Added the IRF3205 transistor to the BOM.
CB
2018-03-24 | Moved a bunch of things around and started placing tracks
TS
2018-03-28 | Placed tracks for Motorcontrollers, Cells and the 9V IC. Check 9V to see if its right as I'm not sure. I also changed high power GNDs to BATT- and generated the net list
CB
2018-03-31 | Changed the location of many terminal blocks after discussion with Tyrel. Also started making proper track sizing for the larger amperages. Removed the 3.3V terminal block as 3.3V will not be used anywhere within the box.
TS
2018-04-04 | Finished the PowerBoardV3. It reads zero errors from the DRC (ladybug) test. Needs to be double checked for trace widths, etc.
CB
2018-04-09 | Added footprint for vertical battery input connector and added four cm to the top of the cutout. Completely Changed the thicknesses. Used areas instead.
TS
2018-04-16 | Cleaned up errors.
CB
2018-04-25 | Created Arm power board pcb with all parts
TS
2018-04-26 | Redesigned arm power board, Tyrel is going to put on usb connectors
CB